## Sheet1
Step # | Action / Task | Owner | Start Date | Due Date | Status | Comments / Notes
1 | Submit formal request for VDI assignment to App Owner | Teja |  |  | Not Started
2 | Assign VDI to App Owner by designated team member | Designated Team Member |  |  | Not Started | PM to identify team member
3 | Coordinate UAT activities with App Owner / Power User / SME | Teja |  |  | Not Started
4 | Prepare and validate UAT environment and VDI readiness | Teja / Infra Team |  |  | Not Started | Ensure App is available in VDI
5 | Execute UAT test cases by App Owner or tester | App Owner / Tester |  |  | Not Started
6 | Record UAT results and document any issues | App Owner |  |  | Not Started
7 | Log defects and notify technical team | App Owner / Teja |  |  | Not Started | Use defect tracking system (e.g., Jira)
8 | Retest after issue resolution (if applicable) | App Owner |  |  | Not Started
9 | Obtain UAT sign-off from App Owner | App Owner |  |  | Not Started
10 | Submit UAT sign-off to Project Manager and stakeholders | Teja |  |  | Not Started
11 | Share final UAT results and completion report | Teja |  |  | Not Started
12 | Update project tracker with UAT completion status | Project Manager |  |  | Not Started
13 | Ensure all UAT activities are completed within 3–4 weeks | Teja / App Owner |  |  | Not Started | Based on project schedule